## Slide 1
Chapter 2
Leading change: a process perspective

## Slide 2
Learning
7. Learning
Leading and managing the people issues
6. Leading and managing the people issues
Key steps in the change process
Managing change involves seven core activities:
1. Recognising the need for change and starting the change process
Recognition and
starting the process
2. Diagnosing what needs to be changed and formulating a vision of a preferred future state
Diagnosis
Planning
3. Planning how to intervene in order to achieve the desired change
Implementation and reviewing progress
4. Implementing plans and reviewing progress
Sustaining the change
5. Sustaining the change

## Slide 3
The start of the change process is recognizing that external events or internal circumstances require or create opportunities for change.
One way of challenging accepted ways of thinking is to involve a number of people in the formulation of the change agenda.
Recognising the need for change and starting the change process (Chapters 3-6)
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
© ImageSource
Leaders sometimes fail to recognise the need for change because they pay insufficient attention to what is happening in the wider environment.
© Macmillan South Africa

## Slide 4
Translating the need or opportunity for change into a desire for change
Deciding who will manage the change
Building effective relationships between change agents and those affected by the change
Other tasks in this first step of the process:
Recognising the need for change and starting the change process
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
© ImageSource

## Slide 5
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Do change managers recognise and listen to informed others?
Is the need for change translated into a desire for change?
Is there a guiding coalition with sufficient power to get things done?
Who formulates the agenda for change? Should others be involved?
Are the managers who will be responsible for making the change work sufficiently well represented in the guiding coalition?
Is sufficient attention been given to building trust and understanding between those leading the change and those who will be affected by it?
© Thinkstock

## Slide 6
Diagnosing what needs to be changed (Chapters 7 & 8)
Identifying the future state
This stage in the process involves reviewing where the organization is today and where it might be in the future.
Reviewing the present state
● identify required changes by diagnosing the cause of a problem or clarifying opportunities
● establish a baseline so that it is clear what is changing
● help define the future direction
Developing a vision for the whole organization
Visioning impact for own part of organization
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning

## Slide 7
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Diagnosing what needs to be changed
Quality of the vision
A shared vision of a more desirable future state can provide a focus for attention and action, and mobilise energy and effort.
People are motivated to achieve goals to which they are committed and try harder and are less willing to give up when goals are clear and realistic.
Problems can arise when those leading the change have a vested interest in a particular outcome or lock on to the first vision they generate, and in so doing lock out the possibility of considering alternatives.
© PhotoDisc

## Slide 8
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Who does the diagnosing - senior managers, consultants or those who will be responsible for making the change work?
Are leaders willing to accept new data or do they only attend to data that defends the status quo or supports their preconceived view?
Does the diagnosis create a realistic and inspiring vision that will motivate others and help direct the change effort?
© Thinkstock

## Slide 9
Planning and preparing for change (Chapters 14 – 24)
Those leading the change need to give attention to:
The overall change strategy
The type and sequence of interventions
The many details that have to be managed
when the end state can be specified
when the end state cannot be specified
The people issues
The long term implications of planning decisions
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
© Thinkstock

## Slide 10
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Is the change strategy appropriate (for example push, pull or a blend of both)?
Is it clear what needs to be done?
Is it clear what kind of intervention(s) would be most effective?
Is sufficient attention being given to anticipating how people may react to the change?
Is sufficient thought being given to the longer term implications of decisions?
© Thinkstock

## Slide 11
Implementing change and reviewing progress (Chapters 24 & 26)
Often change plans are not implemented as intended because those leading the change fail to give sufficient attention to:
Competing goals
Communicating all aspects of the change
Motivating individuals and groups to support the change
Reviewing the change and monitoring progress
Fragmentation and the lack of coordination
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
© CORBIS

## Slide 12
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Do change managers communicate a compelling vision and set realist goals?
Are stakeholders being managed effectively?
Do change managers seek feedback in order to eliminate impediments to implementation?
Is there sufficient coordination between those involved in implementing the change?
© Thinkstock

## Slide 13
Sustaining change (Chapters 27 & 28)
The change strategy
A sustained change is one where “new ways of working and improved outcomes become the norm” and where “the thinking and attitudes behind them are fundamentally altered and the systems surrounding them are transformed in support.”
The NHS Modernisation Agency (2002, p. 12)
It is not enough to think of change in terms of simply reaching a new state.
Sustainability can be affected by many factors:
Leader behaviour post implementation
Churn
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
© MACMILLAN/Paul Briknell

## Slide 14
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Do change managers pursue a change strategy that wins long term commitment?
Do they give sufficient attention to managing the consequences of churn?
Do they reinforce changes post implementation?
Do they avoid declaring victory too soon?
© Thinkstock

## Slide 15
Leading and managing the people issues (Chapters 9 – 13)
Those leading change sometimes approach issues from a purely technical perspective and give insufficient attention to what some refer to as the ‘softer’ people issues.
The way leaders relate to the intended recipients of change
Communication
Trust
Examples of people issues are:
Internal politics and the power of stakeholders to affect outcomes
Motivation and commitment
Support for those who will be affected by the change
Those leading a change need to give constant attention to shaping the political dynamics of change and motivating constructive behaviour.
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
© PhotoDisc
© PhotoDisc/Getty Images

## Slide 16
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Do they act in ways that will promote trust and win commitment?
Do they identify and engage those individuals and groups who can affect the success of the change?
Are they good communicators?
Do leaders empathise with others and understand how they might react to the possibility of change?
Do they empower others to contribute to the change?
Do they support those who are threatened by the change?
© Thinkstock

## Slide 17
Learning (Chapter 29)
Reflect on results and detect errors
BEHAVIOUR
RESULTS
Identify corrective action
Modify behaviour
Single loop learning occurs when leaders focus their attention on detecting errors and acting on this feedback to modify their and other people’s behaviour.
Any new ways of acting are likely to be bound by current thinking and known routines.
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
©ImageSource

## Slide 18
Learning
Double loop learning challenges accepted ways of thinking and behaving and provides a new understanding of situations and events.
Identify beliefs and assumptions that guide decisions and actions
Challenge these beliefs
and assumptions
Revise beliefs and assumptions
Reflect on results
BEHAVIOUR
RESULTS
Covey (1992) argues that:
“The more aware we are of our basic paradigms, maps or assumptions, and the extent to which we have been influenced by our experience, the more we can take responsibility for those paradigms, examine them, test them against reality, listen to others and be open to their perceptions, thereby getting a larger picture and a far more objective view.”(p. 29)
Learning
©Stockbyte/Punchstock

## Slide 19
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning
Questions that might help leaders reflect on how they are managing this stage of the process
Do they monitor the effects of their actions and use this information to guide future decisions?
Are they receptive to feedback from others?
To what extent do they view their own and others’ mistakes as opportunities for learning?
Do they anticipate how others will respond to events before deciding what to do?
Do they attempt to identify and challenge the assumptions that underpin their behaviour?
Are they aware of how decisions that produce positive outcomes in the short term may undermine performance over the long term?
© Thinkstock

## Slide 20
Improving leader performance
are so bound up in a frenetic range of activities that they have little time or no opportunity for observation and reflection
are so committed to a course of action that they fail to recognise evidence which challenges their world view
Leaders can learn to be more effective if they step back and monitor what is going on and use these observations to guide their behaviour. But all too often this does not happen because they:
harbour beliefs about the competence and motives of others that makes it easy for them to dismiss their feedback
are insulated from information about the impact of their decisions by organisation structures, policies and management practices that impede upward communication and foster a climate of organisational silence
are so bound up in and entrapped by a path that progressively limits their scope for decision making that they become path dependant and this excludes path breaking behaviour because they are too involved to adopt an independent external perspective.
©Digital Vision/Getty Images

## Slide 21
Improving leader performance
Leaders need to be aware of these barriers that can make it difficult for them to unlock from an immediate “doing” mode; they need to work hard to adopt an “observing” mode and bring a critical perspective to bear on their everyday practice.
When managing change is viewed as a process and when events, decisions, actions and reactions are seen to be connected leaders are more likely to be able to take action and intervene in ways that can break inefficient patterns and move the change process in a direction that is more likely to deliver superior outcomes.
Leading and managing the people issues
Learning
Recognition and
starting the process
Implementation and reviewing progress
Sustaining the change
Diagnosis
Planning